## Ark1
Task Name | Description | Start | End | Duration (days) | 2023-08-01 | 2023-09-14 | 2023-09-30 | 2023-10-15 | 2023-10-25 | 2023-11-17 | 2023-11-25 | 2023-12-01 | 2024-01-02 | 2024-01-14
1. Preliminary Phase | bar: 2023-08-01
1.1 Formulate learning objectives and start project plan. | Necessary hand-in meeting the requirements from DTU. | 2023-09-01 | 2023-09-11 | 10 | bar: 2023-08-01
1.2 Technical Setup | Prepare GitHub and Overleaf document for the thesis. | 2023-09-01 | 2023-09-11 | bar: 2023-08-01
1.3 Familiarize with Core Concepts | Find papers, read abstracts, and start writing small sections to collect thoughts. | 2023-09-01 | 2023-09-11 | 10 | bar: 2023-08-01
1.4 Acquire sample data | Obtain a little volume of data to become familiar with this type of data. | 2023-09-01 | 2023-09-11 | bar: 2023-08-01
2.Data Processing and Initial Modelling |  |  |  |  | 2023-09-14: 2
2.1 Collect and preprocess more comprehensive data sets | Acquire and work with larger data volumes and preprocess the data, including managing missing values. | 2023-09-14 | 2023-09-30 | 16 | bar: 2023-09-14
2.2 Formulate an initial model for the energy signature of a building. | A deep dive directly into formulating models and test them on data, and documenting observations. These learnings enable me to understand model limitations, interpretability of the models, and intricacies of the data. | 2023-09-14 | 2023-09-30 | 16 | bar: 2023-09-14
2.3 Make an introductory presentation about the project. | Prepare an initial presentation of the project to be presented at the ClimateCluster group at Danmark’s Nationalbank | 2023-09-25 | 2023-09-30 | 5 | bar: 2023-09-14
3. Research |  |  |  |  | 2023-10-15: 3
3.1 Select and Read Relevant Papers on Energy Signature Modelling. | This step serves to give an overview of the topic. | 2023-09-30 | 2023-10-11 | 11 | bar: 2023-09-30 to 2023-10-15
3.2 Select and Read Relevant Papers on Bayesian Regression Analysis. | This step serves to give an overview of the topic and consider practical implementation limitations and benefits. | 2023-10-15 | 2023-10-30 | 15 | bar: 2023-10-15 to 2023-10-25
3.3 Select and Read Relevant Papers on Statistical Clustering. | Multiple clustering methods exist, and this step is to find the most appropriate s.t. the uncertainty is adequately accounted for. Additionally, we can make the clusters more meaningful using houses with energy labels. | 2023-10-20 | 2023-10-31 | 11 | bar: 2023-10-15 to 2023-11-17
3.4 Select and Read Relevant Papers and Reports on Climate Policy Scenarios and Exisiting Climate Navigation Tools | With help from supervisors at Nationalbanken, get familiar with possible policy scenarios. Addtionally, find the climate goals and data from tools like CREEM. | 2023-10-25 | 2023-11-05 | 11 | bar: 2023-10-15 to 2023-11-17
3.5 Write Literature Review on Signature Modelling, Statistical Clustering, and Decision Tools | The different perspectives and choices should be compiled in a rough format. This task can be repeated at the final stage of the thesis writing. | 2023-10-15 | 2023-12-25 | 71 | bar: 2023-09-30 to 2023-11-25
3.6 Begin Writing Theory Section | Describe the theory and relevant concepts to get a coherent report. | 2023-09-30 | 2023-12-01 | 62 | bar: 2023-10-15 to 2023-11-25
3.7 Make Presentations | Target Audience: Nationalbanken. | 2023-11-25 | 2023-12-01 | 6 | bar: 2023-11-25
4. Implementation |  |  |  |  | 2023-10-25: 4
4.1 Implement A Bayesian Signature Model | Implementations initially in Stan. | 2023-10-15 | 2023-10-25 | 10 | bar: 2023-10-15
4.2 Implement a Statistical Clustering Model | Implementations in either R, Python, or Julia | 2023-10-15 | 2023-12-01 | 47 | bar: 2023-10-15 to 2023-11-25
4.3 Implement the Decision Support Framework | Implementation in R, Python, or Julia with excellent visual representations for stakeholders to grasp the concept quickly. | 2023-11-17 | 2023-12-22 | 35 | bar: 2023-11-17 to 2023-12-01
5. Evaluation |  |  |  |  | 2023-11-17: 5
5.1 Evaluate the Results of Each of the Three Modules. | Compare the performance of each module. The focus is always on locating sources of uncertainty, e.g., uncertainty in input data and wrong energy labels, to make adequate and robust decisions in the last module. | 2023-11-17 | 2023-12-22 | 35 | bar: 2023-11-17 to 2023-12-01
5.2 Write Empirical Section | Work on the graphical representation of model results to convey results. On top of that, add tables and related numerics to the report. | 2023-11-17 | 2023-12-22 | 35 | bar: 2023-11-17 to 2023-12-01
5.3 Discussion of the Full Sequence of Modules | Find appropriate metrics to assess performance for each module and the full model pipeline. | 2023-11-25 | 2023-12-22 | 27 | bar: 2023-11-25 to 2023-12-01
6. Ultimate Phase |  |  |  |  | 2024-01-02: 6
6.1 Revisit all sections of the Report. | Revise and read the report thoroughly and keep only the relevant sections in the main report. As new insights might have been gained and the scope altered slightly, only the most relevant sections should be kept in the report. On top of that, a thorough read is necessary. | 2024-01-02 | 2024-01-14 | 12 | bar: 2024-01-02
6.2 Write Conclusion and Abstract | Rrite the conclusion and the abstract based on the final findings. | 2024-01-02 | 2024-01-14 | 12 | bar: 2024-01-02
6.4 Make Presentations | Target Audience: Nationalbanken, which serves as preparation for the thesis defense. | 2024-01-10 | 2024-01-14 | 4 | bar: 2024-01-02
[7 empty] | Presentation 1 |  |  |  | Presentation 2 |  | Presentation 3