## Sheet1
Task Name | Description | Start | End | Duration (days) | 2024-09-01 | 2024-09-14 | 2024-10-01 | 2024-10-14 | 2024-11-01 | 2024-11-14 | 2024-12-01 | 2024-12-14 | 2025-01-01 | 2025-01-14 | 2025-02-01
1. Preliminary Phase | bar: 2024-09-01
1.1 Formulate Learning Objectives and Start Project Plan | Necessary hand-in meeting the requirements from DTU. | 2024-08-26 | 2024-09-12 | 17 | bar: 2024-09-01
1.2 Technical Setup | Prepare Github repository and Overleaf document for the thesis. | 2024-08-26 | 2024-09-12 | 17 | bar: 2024-09-01
1.3 Familiarize with Core Concepts | Read papers, background materials, and interview analysts on credit risk assessment. | 2024-08-26 | 2024-09-12 | 17 | bar: 2024-09-01
1.4 Acquire sample data | Collect and review sample bond prospectuses and familiarize with data. | 2024-08-26 | 2024-09-12 | 17 | bar: 2024-09-01
1.p Initial Project Presentation | Prepare a presentation to showcase initial progress and methodology to Capital Four. (Strawman: outline report sections) | 2024-09-12 | 2024-09-12 | 1 | bar: 2024-09-01
2.Data Processing and Initial Modelling |  |  |  |  | 2024-09-14: 2
2.1 Collect and Preprocess Larger Datasets | Gather larger dataset of bond prospectuses, preprocess them for LLM input, split and clean the documents | 2024-09-13 | 2024-09-30 | 17 | bar: 2024-09-14
2.2 Initial Modelling on Fundamental Scoring | Implement basic pipelines to extract fundamental scores from bond prospectuses, focusing on text preprocessing. | 2024-10-01 | 2024-10-10 | 9 | bar: 2024-10-01
2.p Present preliminary results and expectations | Present findings and update risk log. | 2024-10-10 | 2024-10-12 | 2 | bar: 2024-10-01
3. Research |  |  |  |  | 2024-10-14: 3
3.1 Review Papers on LLMs and LLM Interpretability | Get an overview of the technical aspect and consider practical implementation limitations and possibilities. | 2024-10-13 | 2024-10-31 | 18 | bar: 2024-10-14
3.2 Review Papers on Existing Domain-Specific LLMs in Credit/Finance | Read and summarize relevant academic papers | 2024-10-13 | 2024-10-31 | 18 | bar: 2024-10-14
3.3 Write Litterature Review |  | 2024-10-13 | 2024-10-31 | 18 | bar: 2024-10-14
3.4 Write Theory Section | 2 weeks to finnish all report writing on litterature review and theory. | 2024-11-01 | 2024-11-14 | 13 | bar: 2024-11-01
3.p | Present findings and update risk log. | 2024-11-14 | 2024-11-15 | 1 | bar: 2024-11-01
4. Implementation |  |  |  |  | 2024-10-01: 4
4.1 Implement Initial LLM | Set up a basic LLM to generate fundamental scores from bond prospectuses. | 2024-11-15 | 2024-11-30 | 15 | bar: 2024-11-14
4.2 Fine-Tune LLM on Template to Improve Performance | Fine-tune LLM to follow the expected template (Score + Explanation). | 2024-12-01 | 2025-01-10 | 40 | bar: 2024-12-01 to 2025-01-01
4.3 Fine-Tune LLM with Finance Data to Improve Performance | Fine-tune with financial data to potentially enhance understanding of domain-specific language and improve scoring. | 2024-12-01 | 2025-01-10 | 40 | bar: 2024-12-01 to 2025-01-01
4.4 Reiterate 2.1, 2.2, 3, and 4 based on learnings |  | 2024-10-01 | 2025-01-10 | 101 | bar: 2024-10-01 to 2025-01-01
4.5 Finalize theory and litterature review section |  | 2025-01-01 | 2025-01-20 | 19 | bar: 2024-12-01 to 2025-01-01
4.6 Implement Decision Support Framework | Implement a system to visualize and compare LLM-generated scores with manual scores. | 2024-12-31 | 2025-01-10 | 10 | bar: 2025-01-01
4.p | Present findings and update risk log. | 2025-01-10 | 2025-01-11 | 1 | bar: 2025-01-01
5. Evaluation |  |  |  |  | 2024-11-14: 5
5.1 Evaluate LLM Scores | Compare the LLM-derived scores to human analyst scores to evaluate accuracy, reliability, and interpretability. | 2025-01-11 | 2025-01-20 | 9 | bar: 2025-01-01 to 2025-01-14
5.2 Write Empirical Section | Document analysis/findings, compare automated scores with manual scoring on metrics like accuracy and time efficiency. | 2024-11-15 | 2025-01-20 | 66 | bar: 2024-11-14 to 2025-01-14
5.3 Discuss Ethical and Practical Implications | Analyze ethical concerns of LLM usage in credit scoring and its practical integration into existing workflows. | 2025-01-21 | 2025-01-30 | 9 | bar: 2025-01-14
5.p | Present findings and update risk log. | 2025-01-30 | 2025-02-02 | 3 | bar: 2025-01-14
6. Ultimate Phase |  |  |  |  | 2025-01-14: 6
6.1 Finalize Report and Revise Based on Feedback | Complete the thesis draft and revise based on supervisor feedback. | 2025-01-21 | 2025-02-04 | 14 | bar: 2025-01-14 to 2025-02-01
6.2 Conclusion and Abstract | Write conclusion and abstract. | 2025-01-31 | 2025-02-04 | 4 | bar: 2025-02-01
6.p Final Presentation | Prepare and deliver the final presentation, summarizing findings and practical implications. | 2025-02-05 | 2025-02-07 | 2 | bar: 2025-02-01

## Risks
Task Name | Risk | Risk Mitigation | Start | End
1. Preliminary Phase
1.1 Formulate Learning Objectives and Start Project Plan |  |  | 2024-09-02 | 2024-09-12
1.2 Technical Setup |  |  | 2024-09-02 | 2024-09-12
1.3 Familiarize with Core Concepts |  |  | 2024-09-02 | 2024-09-12
1.4 Acquire sample data |  |  | 2024-09-02 | 2024-09-12
1.p Initial Project Presentation |  |  | 2024-09-12 | 2024-09-12
2.Data Processing and Initial Modelling
2.1 Collect and Preprocess Larger Datasets |  |  | 2024-09-13 | 2024-09-30
2.2 Initial Modelling on Fundamental Scoring |  |  | 2024-10-01 | 2024-10-10
2.p Present preliminary results and expectations |  |  | 2024-10-10 | 2024-10-12
3. Research
3.1 Review Papers on LLMs and LLM Interpretability |  |  | 2024-10-13 | 2024-10-31
3.2 Review Papers on Existing Domain-Specific LLMs in Credit/Finance |  |  | 2024-10-13 | 2024-10-31
3.3 Write Litterature Review |  |  | 2024-10-13 | 2024-10-31
3.4 Write Theory Section |  |  | 2024-11-01 | 2024-11-14
3.p |  |  | 2024-11-14 | 2024-11-15
4. Implementation
4.1 Implement Initial LLM |  |  | 2024-11-15 | 2024-11-30
4.2 Fine-Tune LLM on Template to Improve Performance |  |  | 2024-12-01 | 2025-01-10
4.3 Fine-Tune LLM with Finance Data to Improve Performance |  |  | 2024-12-01 | 2025-01-10
4.4 Reiterate 2.1, 2.2, 3, and 4 based on learnings |  |  | 2024-10-01 | 2025-01-10
4.5 Finalize theory and litterature review section |  |  | 2025-01-01 | 2025-01-20
4.6 Implement Decision Support Framework |  |  | 2024-12-31 | 2025-01-10
4.p |  |  | 2025-01-10 | 2025-01-11
5. Evaluation
5.1 Evaluate LLM Scores |  |  | 2025-01-11 | 2025-01-20
5.2 Write Empirical Section |  |  | 2024-11-15 | 2025-01-20
5.3 Discuss Ethical and Practical Implications |  |  | 2025-01-21 | 2025-01-30
5.p |  |  | 2025-01-30 | 2025-02-02
6. Ultimate Phase
6.1 Finalize Report and Revise Based on Feedback |  |  | 2025-01-21 | 2025-02-04
6.2 Conclusion and Abstract |  |  | 2025-01-31 | 2025-02-04
6.p Final Presentation |  |  | 2025-02-05 | 2025-02-07